# Therapist Online Revenue Roadmap (Updated)

Goal: Launch e-book and online course, build email list, and create passive income streams

## Phase 1: E-Book Completion (Weeks 1–2)

- Finish content & worksheets

- Proofread & polish

- Design PDF (Canva / InDesign)

- Create mini lead magnet version for email capture
Outcome: Ready-to-download e-book + freebie version

## Phase 1.5: Website Refinement (Weeks 1–3, overlaps Phase 1)

- Upload website content: About, Services, Course + E-book info

- Integrate lead capture forms for free downloads

- Connect Stripe for payments (already done)

- Optimize pages for clarity, conversion, and SEO

- Add testimonials / social proof if available
Outcome: Professional, conversion-ready website that funnels visitors into your email list and sales pages

## Phase 2: Course Recording (Weeks 3–6)

- Finalize course script and slides

- Record modules (5–10 min each)

- Edit videos + add slides / captions

- Create workbook / PDF companion
Outcome: Complete course content ready for platform upload

## Phase 3: Platform Setup (Weeks 5–7)

- Choose platform (Podia recommended)

- Upload videos & materials

- Set up pricing tiers (Base $97 / Premium $147 / VIP $197)

- Build course welcome sequence + sales page
Outcome: Course is live-ready for first launch

## Phase 4: Email List & Lead Capture (Weeks 2–7, ongoing)

- Embed lead capture forms on website

- Offer free e-book / guide as lead magnet

- Segment email list (interested in parent support vs course buyers)

- Draft 3–5 email nurture sequence: tips + soft course pitch
Outcome: Growing engaged email list ready for launch

## Phase 5: Marketing & Launch (Weeks 8–10)

- Pre-launch emails to list

- Social media mini-campaigns (tips, short videos, mini workshops)

- Offer early-bird bonuses for first buyers

- Host free webinar or Q&A for lead engagement
Outcome: First wave of course sales + testimonials

## Phase 6: Evergreen Sales (Week 11 onward)

- Keep course available on platform

- Weekly/biweekly emails linking free content → course

- Continue social content → lead magnet → course funnel

- Launch occasional mini-promotions / bundle e-books
Outcome: Passive income stream established + continuous lead generation